## Sheet1
Outstanding Issue/Concerns
Demosphere
Status | Date Resolved | Date Reported | Short Name Issue | Description | Short Term Work Around | Issue Resolution | Additional Questions:
Open |  | 2018-07-01 | Birth Cert Check Off | With the transfer of data from L1, the BCs were not checked off. Fields from L1 did not match field in Demosphere. | 1) Mark all of 1 by 1. 2) Use button at top of screen and check off all records at once.
Open |  | 2018-07-15 | Coaches NOT tranfered to Demosphere | The coaches did not get transferred when the players did | WYSA has indicated the coaches should be in new system by 7/28/18 **** Rosters can not be approved with a coach who does not have Risk Management up-to-date. | Wait for coaches to get loaded | 1) If a parent was transferred and is also a coach, will there be separate records or will the records be merged. 2) Can Risk Management be processed out of the Demosphere system?
CLOSED |  | 2018-07-12 | Player Pass Alignmnet is OFF |  | Turn the card stock player passes over and print on the back side so all of the inforamtion is eligible. ****Even when printing on the back, the alignment is off due to perfornation on the right side of the pass.
OPEN | 2018-07-28 | 2018-07-01 | Player Pass Pictures | Were not transferred to new system. | If pictures were added after player transfer, they are not showing up. If they show up pictures can not be edited. | When printing the player passes make sure the picture is clear enough to idenify the player. (Doris) I found this statement in the Demosphere Q&A page: Sizing Player Passes Photos When uploading a photo it is critical to size the photo prior to uploading it. The correct sizing is 66x70. A webbased photo editing software solution we recommend is pixlr.com | 1) Picture is not longer required when registering. *** Check if you need to turn this on for your club.
Open |  | 2018-07-17 | Processing Fee | Process has changed. Make sure to review how your clubs wishes to handle this. | Looks like there is only one standard fee which can be applied to each registeration process and not allowing for % to be applied.
Will check on |  | 2018-07-25 | Pulling team inforamtion into EC Team Application Form | Would like to have the Application Form retrieve the team data from the database. | Will check into |  | Would like to have work the same as the State League Application
Request |  | 2018-07-25 | Share the Wealth | Have WYSA pass along items they know about to everyone via email rather than having everyone wondering and calling in. | Save Time and Effort | Send out Email when the issue has a resoluntion
Check on | Jenna Ryan | 2018-07-27 | Number of Coaching Staff listed on Roster | Appears the Roster will only list 3 coaching staff members when printed. |  |  | Is there a limit to the number of coaching staff members allowed?
Open | Jay D | 2018-07-27 | Physician Phone number on Mobile device | If you require a physician's phone number, and try to register through a mobile device, the phone number keeps getting wiped out and won't let the users continue.
Question | Jenna Ryan | 2018-07-24 | Out-of-State Players | Do they still need to be approved by the state office? | Currently there is no requirement.