## Sheet1
Problem Type (Building/Field/Facility/Equipment) | Problem Description | Corrective Action | Estimated Cost | Estimated Effort (Man-hours) | Suggested Provider (Internal vs. Contractual) | Priority | When to Accomplish | Planned Year
Building | Roof fascia board is deteriorated | Replace fascia board on main concessions building |  | 4 |  |  | July-October
Building | Concession building paint is faded and failing | Repaint concession building
Building | Old scoreboard does not work | Remove old scoreboard from main concessions building | 0 | 3 | Volunteers |  | July-October
Building | Training equipment is exposed to weather due to lack of space. | Construct small storage facility on existing concrete slab at Murray field to house just training equipment. Items such as pitching machine, cords, protective screens, etc.
Building | Underutilized storage facility on 2nd floor. | Modify by enlarging existing team equipment storage lockers to include new shelving, etc. for just four - six teams on second floor of concessions building. |  |  | Volunteers
Building | Murray Field Dugout soffits are deteriorated; have holes in them. | Replace and preserve soffit plywood on both dugouts.
Building | Old freezer in concession stand does not work | Remove door and take freezer to recycling |  |  | Volunteer |  | Anytime
Building | Rwfrigerator in concession stand is not keeping beverages cold. | Replace with a new refrigerator
Building | Upper Storage building fascia board is deteriorated and has carpenter bees | Replace fascia board on upper stroagae building.
Building | Access to 2nd floor of 1st base dugout on Murray field is hazardous as stairs are not per code. | Remove stairs and install new stairs with landing.
Building | Access door to 2nd floor of 1st base dugout on Murray Field is deteriorated. | Replace door
Equipment | Pepsi fridge compressor is noisy | Replace refrigerator in concession stand |  |  | Contract w/ Beverage Company |  | Anytime
Equipment | Current base system is old and poses potential safety hazard on Gabarro and Murray fields | Replace Base systems | 400 | 4 |  |  | April | 2020
Equipment | Lack of hand tools impedes timely repair and maintenance of facility equipment | Purchase tool boxes and hand tools for both storage facilities at South Side. | 200 | 2 |  |  | Anytime
Facility | Each spring snow melt causes muddy ditch | Install crushed stone drainage in depression between road and Murray Field | 4000 |  | Contracted Wade Landscaping
Facility | Existing tree drops twigs, branches and seedlings on field | Cut down tree outside home plate at Murray Field |  |  |  |  | July-November
Facility | Garden is overgrown and unsightly | Remove old flowers/weeds and rebuild garden outside batting cage to include new shrubs, flowers and mulch. |  |  | Volunteers
Facility | Red Murray monument is not visible to public | Remove shrubs and trim plantings and reconstruct garden around Red Murray monument |  |  | Volunteers
Facility | Existing garden is unsightly | Remove and replace rotting timers around Adam Loudon Memorial granite bench |  |  | Volunteers
Facility | Total amount of Field equipment is unknown | Clean storage area and inventory field equipment |  | 4 | Volunteers |  | September/October
Facility | Park entrance sign is not entirely visible | Trim and/or remove some shrubs and consider new plantingd to make sign visible | 100 | 3 | Volunteers |  | April-October
Facility | Handicapped parking spaces are nearly invisible. | Repaint Handicap Parking spaces
Field | Fencing is deteriorated and causes safety hazard to players | Replace 10' high fence between 1st base dugout and backstop on Gabarro Field |  |  | Contract
Field | Frost heaves have caused breakdown of fence integrity | Reset fence posts and fencing of enclosure outside 3rd base dugout at Gabarro Field
Field | Poor drainage on Gabarro Field during spring melt makes use of field uncertain for start of spring season | Replace outfield of Gabarro Field | 8450 |  | Contracted Hillside (?) for work |  | July/August | 2019
Field | Previous fence post footing of left filed gate access at Murray field is hazard | Remove fence post footing | 0 | 1 | Volunteer |  | July-November
Field | Inadequate support behind backstop at Murray field doesn't prevent field erosion | Construct support using timbers (4x4) hold prevent field erosion issues |  |  |  |  | July/August
Field | Outfields are uneven each spring and present injury hazard | Consider purchasing fill for divots to help level and roller to flatten and smooth each spring. |  |  | Contract |  | September/October
Field | Outfield fencing posts on Murray Field have been pushed out of ground due to frost heaves and fence does not reach ground | Remove/replace apprx. 125' of posts in ground and rehang fencing
Filed | Warning tracks and areas inside fences in foul territory on both Gabarro and Murray fields is overgrown and needs attention | Remove vegetation and install new cinder stone along fencing on both fields.

## Supplies
Item | Location | Supplier | Qty | Each | Cost
Screen drag | Murray Field | M.A.S.A. | 1 | 250 | 250
Pudlle pads | Both | M.A.S.A. | 2 | 90 | 250
Water Hog Pad | Murray Field |  |  |  | 250
Repair Hitting Net Legs |  |  |  |  | 250
Turface 10 bags | Both |  |  |  | 250
Nail Drag Tines |  |  |  |  | 250
Field Roller |  |  |  |  | 250
250
250
Suppliers |  |  |  |  | 250
Beacon Athletics |  |  |  |  | 250
M.A.S.A. |  |  |  |  | 250
On Deck Sports |  |  |  |  | 250
250
250
250
250
250
250
250
250
250